## Planned_vs_Actual_Sprint
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
S1 | S1 | US-001 | Environment Setup & DB Configuration (Spring Boot, Hibernate) | MUST HAVE | No Dependency | Intern | Completed
S1 | S1 | US-002 | Vendor Data Modeling & Schema Design | MUST HAVE | US-001 | Intern | Completed
S2 | S2 | US-003 | Vendor Registration & Profile Management Module | MUST HAVE | US-002 | Intern | Completed
S2 | S2 | US-004 | Procurement Workflow Automation Engine | MUST HAVE | US-003 | Intern | Completed
S3 | S3 | US-005 | Purchase Order Tracking System | MUST HAVE | US-004 | Intern | Completed
S3 | S3 | US-006 | Analytics & JasperReports Integration | MUST HAVE | US-005 | Intern | Completed
S4 | S4 | US-007 | Role-Based Access & Security Layer | MUST HAVE | US-006 | Intern | Completed
S4 | S4 | US-008 | Deployment & Final Testing | MUST HAVE | US-007 | Intern | Completed

## Sprint_1_Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity Status | Original Estimate Effort (In Hours) | Day 1 Pending Hours | Day 2 Pending Hours | Day 3 Pending Hours | Day 4 Pending Hours | Day 5 Pending Hours | Day 6 Pending Hours | Day 7 Pending Hours | Day 8 Pending Hours | Day 9 Pending Hours | Day 10 Pending Hours | Day 11 Pending Hours | Day 12 Pending Hours | Day 13 Pending Hours | Day 14 Pending Hours
US-001 | 1 | Spring Boot Project Setup & DB Config | 30-Dec-2025 | 03-Jan-2026 | Intern | 3-Completed | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 2 | Vendor Entity & Database Schema Design | 31-Dec-2025 | 04-Jan-2026 | Intern | 3-Completed | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0

## Sprint_2_Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity Status | Original Estimate Effort (In Hours) | Day 1 Pending Hours | Day 2 Pending Hours | Day 3 Pending Hours | Day 4 Pending Hours | Day 5 Pending Hours | Day 6 Pending Hours | Day 7 Pending Hours | Day 8 Pending Hours | Day 9 Pending Hours | Day 10 Pending Hours | Day 11 Pending Hours | Day 12 Pending Hours | Day 13 Pending Hours | Day 14 Pending Hours
US-003 | 1 | Vendor Registration & Compliance Module | 13-Jan-2026 | 17-Jan-2026 | Intern | 3-Completed | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 2 | Procurement Workflow & Approval Logic | 14-Jan-2026 | 18-Jan-2026 | Intern | 3-Completed | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint_3_Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity Status | Original Estimate Effort (In Hours) | Day 1 Pending Hours | Day 2 Pending Hours | Day 3 Pending Hours | Day 4 Pending Hours | Day 5 Pending Hours | Day 6 Pending Hours | Day 7 Pending Hours | Day 8 Pending Hours | Day 9 Pending Hours | Day 10 Pending Hours | Day 11 Pending Hours | Day 12 Pending Hours | Day 13 Pending Hours | Day 14 Pending Hours
US-005 | 1 | Purchase Order Lifecycle Tracking | 27-Jan-2026 | 31-Jan-2026 | Intern | 3-Completed | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 2 | JasperReports Cost Optimization Reports | 28-Jan-2026 | 01-Feb-2026 | Intern | 3-Completed | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint_4_Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity Status | Original Estimate Effort (In Hours) | Day 1 Pending Hours | Day 2 Pending Hours | Day 3 Pending Hours | Day 4 Pending Hours | Day 5 Pending Hours | Day 6 Pending Hours | Day 7 Pending Hours | Day 8 Pending Hours | Day 9 Pending Hours | Day 10 Pending Hours | Day 11 Pending Hours | Day 12 Pending Hours | Day 13 Pending Hours | Day 14 Pending Hours
US-007 | 1 | Role-Based Access Control Implementation | 10-Feb-2026 | 14-Feb-2026 | Intern | 3-Completed | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0
US-008 | 2 | Deployment & System Testing | 11-Feb-2026 | 15-Feb-2026 | Intern | 3-Completed | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Impediments_Log
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 4 | Hibernate mapping errors | Fixed entity annotations and DB schema sync
Sprint 2 | Day 8 | Workflow approval logic complexity | Redesigned multi-level approval structure
Sprint 3 | Day 6 | JasperReports integration issues | Updated report template and datasource config
Sprint 4 | Day 9 | Role permission conflicts | Implemented RBAC validation and testing

## Retrospective
SL # | Sprint # | Sprint Start Date | Sprint End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 29-Dec-2025 | 11-Jan-2026 | Intern | Better DB planning | Ignoring validation errors | Regular mentor reviews | Stable schema created
2 | Sprint 2 | 12-Jan-2026 | 25-Jan-2026 | Intern | Modular workflow coding | Hardcoded approval logic | Unit testing workflows | Reduced logical bugs
3 | Sprint 3 | 26-Jan-2026 | 08-Feb-2026 | Intern | Report optimization | Skipping report testing | Integration testing | Accurate cost reports generated
4 | Sprint 4 | 09-Feb-2026 | 23-Feb-2026 | Intern | Security validation | Overcomplicating roles | Performance tuning | Secure system deployment achieved